## Sheet1
ECB (Electric Consumption Billing) | Duration |  | Start Date |  | End Date
| 15 Weeks? |  | August 22, 2024 |  | December 12, 2024
Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
1. Project Planning and Requirements
- Define Project Scope
- Gather Requirements
- Finalize Functional Requirements
2. System Design
- Database Design
- UI/UX Design
3. Development
- User Authentication Module
- Customer Profile Management
- Consumption Data Entry Module
- Billing Calculation and Invoice Gen.
- Payment Processing Module
- Reporting and Analytics
4. Testing
- Unit Testing
- Integration Testing
- User Acceptance Testing (UAT)
5. Deployment and Documentation
- Deployment
- User Guide/Documentation
- Project Handover